## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Bob Smith | 555-5676 | 8 | Mon - Fri
Sue Jones | 555-2567 | 8 | Mon - Fri
Tim Thomas | 555-2243 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Bob Smith
Documentation Developer | Bob Smith
Data Warehouse Developer | Sue Jones
ETL developer | Sue Jones
Cube Developer | Sue Jones
Report Developer | Sue Jones
Testers | Tim Thomas
Release Manager | Tim Thomas

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type
DWPubsSales | Data Warehouse | Pubs OLTP | Database | Database
DWPubsSales.dbo.FactSales | Fact Table | Pubs.dbo.Sales | Table | Table
DWPubsSales.dbo.OrderNumber | Dimension Key Column | Pubs.dbo.Sales.dbo.ord_num | varchar(20) | nvarchar(50)
DWPubsSales.dbo.OrderDateKey | Dimension Key Column | Pubs.dbo.Sales.dbo.ord_date | datetime | int
DWPubsSales.dbo.FactSales.TitleKey | Dimension Key Column | Pubs.dbo.Sales.Title_id | varchar(6) | int
DWPubsSales.dbo.StoreKey | Dimension Key Column | Pubs.dbo.Sales.Stor_id | char(4) | int
DWPubsSales.dbo.FactSales.SalesQuantity | Measure Column | Pubs.dbo.Sales.Qty | smallint | int
DWPubsSales.dbo.DimStores | Dimesion Table | Pubs.dbo.stores | Table | Table
DWPubsSales.dbo.DimStores.StoreKey | Dimension Key Column | Generated | na | int
DWPubsSales.dbo.DimStores.StoreId | Dimension Column | Pubs.dbo.stores.stor_id | char(4) | nchar(4)
DWPubsSales.dbo.DimStores.StoreName | Dimension Column | Pubs.dbo.stores.stor_name | varchar(40) | nvarchar(50)
DWPubsSales.dbo.DimTitles | Dimesion Table | Pubs.dbo.titles | Table | Table
DWPubsSales.dbo.DimTitles.TitleKey | Dimension Key Column | Generated | na | int
DWPubsSales.dbo.DimTitles.TitleId | Dimension Key Column | Pubs.dbo.titles.title_id | varchar(6) | nchar(6)
DWPubsSales.dbo.DimTitles.TitleName | Dimension Column | Pubs.dbo.titles.title | varchar(80) | nvarchar(100)
DWPubsSales.dbo.DimTitles.TitleType | Dimension Column | Pubs.dbo.titles.type | char(12) | nvarchar(50)
DWPubsSales.dbo.DimTitles.PublisherKey | Dimension Column | Pubs.dbo.titles.pub_id | char(4) | int
DWPubsSales.dbo.DimTitles.TitlePrice | Dimension Column | Pubs.dbo.titles.price | money | decimal(18,4)
DWPubsSales.dbo.DimTitles.PublishedDateKey | Dimension Column | Pubs.dbo.titles.pubdate | datetime | int
DWPubsSales.dbo.DimPublishers | Dimesion Table | Pubs.dbo.publishers | Table | Table
DWPubsSales.dbo.DimPublishers.PublisherKey | Dimension Key Column | Generated | na | int
DWPubsSales.dbo.DimPublishers.PublisherId | Dimension Key Column | Pubs.dbo.publishers.pub_id | char(4) | nchar(4)
DWPubsSales.dbo.DimPublishers.PublisherName | Dimension Column | Pubs.dbo.publishers.pub_name | varchar(40) | nvarchar(50)
DWPubsSales.dbo.FactTitlesAuthors | Dimesion Table | Pubs.dbo.titleauthor | Table | Table
DWPubsSales.dbo.FactTitlesAuthorsKey | Dimension Key Column | Pubs.dbo.titleauthor.title_id | na | int
DWPubsSales.dbo.FactTitlesAuthors.TitleKey | Dimension Key Column | Pubs.dbo.titleauthor.au_id | na | int
DWPubsSales.dbo.FactTitlesAuthors.AuthorOrder | Dimension Column | Pubs.dbo.titleauthor.au_ord | tinyint | int
DWPubsSales.dbo.DimAuthors | Dimesion Table | Pubs.dbo.authors | Table | Table
DWPubsSales.dbo.DimAuthors.AuthorKey | Dimension Key Column | Generated | na | int
DWPubsSales.dbo.DimAuthors.AuthorId | Dimension Key Column | Pubs.dbo.authors.au_id | varchar(11) | nchar(11)
DWPubsSales.dbo.DimAuthors.AuthorName | Dimension Column | Pubs.dbo.authors.au_fname | varchar(40) | nvarchar(100)
DWPubsSales.dbo.DimAuthors.AuthorName | Dimension Column | Pubs.dbo.authors.au_lname | varchar(20) | na
DWPubsSales.dbo.DimAuthors.AuthorState | Dimension Column | Pubs.dbo.authors.state | char(2) | nchar(2)
DWPubsSales.dbo.DimDates | Dimesion Table | na | na | Table
DWPubsSales.dbo.DimDates.DateKey | Dimension Column | na | na | int
DWPubsSales.dbo.DimDates.Date | Dimension Column | na | na | datetime
DWPubsSales.dbo.DimDates.DateName | Dimension Column | na | na | nvarchar(50)
DWPubsSales.dbo.DimDates.Month | Dimension Column | na | na | int
DWPubsSales.dbo.DimDates.MonthName | Dimension Column | na | na | nvarchar(50)
DWPubsSales.dbo.DimDates.Quarter | Dimension Column | na | na | int
DWPubsSales.dbo.DimDates.QuarterName | Dimension Column | na | na | nvarchar(50)
DWPubsSales.dbo.DimDates.Year | Dimension Column | na | na | int
DWPubsSales.dbo.DimDates.YearName | Dimension Column | na | na | nvarchar(50)
Object Name | Description | Source | Source Type | Destination Type

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description